## Starportal
Task Name | Estimate | Start Date | Task Owner | Assumptions / Known Issues / Notes
Project Problem Statement | 1 days | 2018-07-14 | Chris Andersen
Project Plan | 1 days | 2018-07-14 | Chris Andersen
Get Project Approved | 1 days | 2018-07-14 | Chris Andersen
Document Requirements | 1 days | 2018-07-15 | Chris Andersen
Finalize Requirements | 1 days | 2018-07-15 | Chris Andersen
Design Classes | 1 days | 2018-07-15 | Chris Andersen
Document Technical Design | 1 days | 2018-07-15 | Chris Andersen | Include version control system, language, IDE, etc.
Design ASCII Art/ UI | 1 days | 2018-07-16 | Chris Andersen
Create Code Classes | 1 days | 2018-07-17 | Chris Andersen
Create Storyboard | 1 days | 2018-07-18 | Chris Andersen
Write code for features | 2 days | 2018-07-19 | Chris Andersen
Implement Storyboard | 1 days | 2018-07-21 | Chris Andersen
Test Playthroughs / Edit | 1 days | 2018-07-22 | Chris Andersen
Finalize Code | 1 days | 2018-07-23 | Chris Andersen
Code Review | 1 days | 2018-07-24 | Chris Andersen
Test Code - Development | 1 days | 2018-07-25 | Chris Andersen
Deploy Program | 1 days | 2018-07-26 | Chris Andersen | Acquire Test Data
Test Deployment | 1 days | 2018-07-27 | Chris Andersen
Fix Issues | 2 days | 2018-07-28 | Chris Andersen
Submit Program | 1 days | 2018-07-30 | Chris Andersen